Regional Hospitality Leadership Conference

Presentation source document | Fictional training scenario

Purpose: This document contains the complete content needed to recreate a customer presentation when the original PowerPoint file was not saved.

Event overview

| Item | Confirmed detail |
| --- | --- |
| Event | Regional Hospitality Leadership Conference |
| Attendance | 120 guests |
| Main venue | Grand Ballroom |
| Additional room | Meeting Room 2 |
| Programme | 9:00 AM to 4:30 PM |
| Room inspection | 7:30 AM |
| Customer update | One consolidated organiser update before guest arrival |

The presentation should reassure the customer that the hotel understands the conference flow, guest experience priorities, and operational preparation required across the day.

Recommended presentation story

- Open with the event purpose and the guest experience the hotel intends to support.

- Show the day as a clear journey from arrival through the closing session.

- Explain how the venue, catering, equipment, and hotel teams support each stage.

- Make responsibilities and readiness checks visible without exposing unnecessary internal detail.

- Close with the agreed next steps and the items that still require customer confirmation.

Programme and guest journey

| Time | Programme moment | Guest experience focus |
| --- | --- | --- |
| 8:15-9:00 AM | Registration and arrival | Clear welcome point, directional signs, coffee available |
| 9:00-9:20 AM | Welcome | Confident opening, microphones tested, screen ready |
| 9:20-11:00 AM | Keynote and discussion | Comfortable room temperature and clear sound |
| 11:15 AM-12:30 PM | Breakout sessions | Smooth movement between rooms and visible support |
| 12:30-1:30 PM | Lunch | On-time service and clear dietary labels |
| 1:30-4:00 PM | Panel and workshops | Reliable equipment and quick issue response |
| 4:00-4:30 PM | Closing | Clear final message and departure guidance |

Venue and equipment

- Grand Ballroom: theatre seating for 120 guests.

- Meeting Room 2: breakout and organiser workspace.

- Two handheld microphones.

- Presentation screen and connection check before the 7:30 AM room inspection.

- Registration desk positioned outside the Grand Ballroom.

- Directional signs from the hotel entrance to the conference area.

Hotel teams and responsibilities

| Team | Presentation message |
| --- | --- |
| Events | Coordinates the event plan and the consolidated organiser update |
| Front Office | Supports arrival, directions, and guest questions |
| Banqueting | Prepares room layout and service transitions |
| Catering | Delivers coffee, lunch, and dietary labels at confirmed times |
| Engineering | Checks temperature, power, screen, and microphones |
| Housekeeping | Confirms conference-area readiness and presentation standards |

Guest experience commitments

- A clear arrival experience with one visible registration point.

- A comfortable room with temperature checked before guest arrival.

- Equipment tested before the organiser receives the readiness update.

- Food and beverage service aligned to the programme.

- One consolidated organiser update instead of separate messages from multiple teams.

- Open issues recorded with an owner and deadline before the next programme stage.

Items still requiring confirmation

- Final customer-approved decoration palette.

- Final speaker list and presentation order.

- Confirmed dietary quantities.

- The named person authorised to approve final room readiness.

- The escalation contact for urgent customer decisions on event day.

Presentation requirements

- Use a concise customer-facing story rather than copying this document paragraph by paragraph.

- Use visuals for the guest journey, venue setup, and team coordination.

- Keep operational detail accurate and clearly distinguish confirmed information from items still requiring confirmation.

- End with a review slide covering decisions, owners, deadlines, and missing information.

Suggested closing message

The hotel team is prepared to support a smooth conference experience from arrival to closing. Final decoration, speaker, dietary, readiness-approval, and escalation details remain to be confirmed before the event presentation is treated as final.