# Friday Issues Report

Reference file 2 of 4 | Operational issues from the previous conference

This report records what was observed. Some resolutions and owners were not captured.

| Issue reported | Impact and recorded response |
| --- | --- |
| Conference hall cooling | The ballroom was warmer than expected during final preparation. Facilities was asked to inspect the system, but the final temperature and closure time were not recorded. |
| Catering delay | Morning coffee arrived later than planned. The Events team arranged a temporary water station while waiting for the delivery. |
| Microphones unavailable | The two requested handheld microphones were not in the ballroom. Replacement equipment was located, but the owner who confirmed it was not recorded. |
| Organiser communication | The organiser received separate updates from Events, Catering, and Facilities. Some messages repeated information and used different status descriptions. |
| Action ownership | Several actions were discussed, but one shared list of owners and deadlines was not maintained. |

# What worked

- Teams responded quickly once the issues were visible.

- A temporary refreshment arrangement reduced disruption.

- Replacement audio equipment was found before the main programme.

# What needs improvement

- Complete checks earlier and record the result.

- Use one readiness update for the organiser.

- Record an owner, deadline, status, and escalation path for each issue.

Unresolved in this report: final cooling resolution, named equipment owner, and final incident closure.